		Summary Week Report

Project	Real-Time Bridge Monitoring			Week	02
Responsible	Andrea Bottoli			Date	12.01.2014

## Executive Summary

Timeliness

General Project Status	Fulfillment of Next Milestone
on track	on schedule

## Results This Week

Activity Owner(s)	Activity	Workload	Fore cast	Result / Comment
All	Tuesday Meeting	1	2	Internal meeting to discuss problems and project status
All	Week Report	1	1	Write the week report
All	Final Questionnaire	1	1	Write the final questionnaire
All	Class Lecture	3	3	In class for the final presentations of the DSD course
All	Final Presentation	1	1	Final Presentation
Andrea Bottoli, Lorenzo Pagliari	Prepare presentation	6	6	Prepared the final presentation in a statical way
Andrea Bottoli, Lorenzo Pagliari	Project Plan	4	4	Updated the project plan
Andrea Bottoli, Marko Brcic	Desing Doc	3	3	Updated the design documentation
Dzana Kujan, Nikola Radisavljevic	Front End	10	10	Finalized frontend
Andrea Bottoli	Summary Week Report	2	2	Write the summary week report
Andrea Bottoli	Requirements Doc	1	1	Updated the requirements documentation
Andrea Bottoli	Fill DB	7	7	Filled the remote DB
Andrea Bottoli	Final Project Report	2	2	Write the final project report
Marko Brcic	Prezi Presentation	10	10	Put the final presentation in Prezi for additional animations
Marko Brcic	Deployment	2	2	Deployment of the final project
Jorn Tillmanns	Documentation	8	8	Finalize documentation
Miraldi Fifo	Test Report	8	8	Finalized Test Report

## Activities Planned for Next Period

Activity Owner(s)	Activity	Work load	Result / Comment
All	Tuesday Meeting	2	Internal meeting to discuss problems and project status
All	Finalize Documents	10	Finalize all the documents and put them on the project site
All	Final Product	3	Made the last changes to the product and put in on the project site

## Comments / Experiences / Problems

- The DB is very huge: at this moment, we have more than 26'000'000 tuples in Raw_Data table
- Founded some bugs in the project; we are fixing them
- Sometimes the VM is down, so we cannot use the DB and we have to stop our work
- This week Andrea and Lorenzo went to MDH and spent some very good time with Swedish team

## Metrics

Milestones

Id	Milestone Description	Responsible Dept./Initials	Finished week				Metr	Rem
			Plan	Forecast		Actual
				Week	+/-
M-001	Project Plan & Vision	All	42	42	0	43
M-002	Requirements gathering	All	43	43	0	43
M-003	Requirements document	All	43	44	1	43
M-004	System Design	All	43	44	0	43
M-005	Requirement Document	All	44	44	0	44
M-006	Design Document	All	44	44	0	44
M-007	Status Report	All	44	44	0	44
M-008	Organize Repository	Marko Brcic	45	45	0	45
M-009	Team Policies	Marko Brcic	45	45	0	45
M-010	Share telephone number	All	45	45	0	45
M-011	Modify Requirement Doc	Dzana Kujan	45	46	1	45
M-012	Modify Design Doc	Lorenzo Pagliari	45	46	1	45
M-013	Setup tools on PC	All	45	45	0	45
M-014	Change DB	Jorn Tillmanns	45	45	0	45
M-015	Implementation Parser	Jorn Tillmanns	45	45	0	45
M-016	Implementation DAO	Jorn Tillmanns	45	45	0	45
M-017	Start Implementation Math	Andrea Bottoli	45	46	1	45
M-018	Test Parser	Miraldi Fifo	46	47	0	46
M-019	Test Classes alpha prot.	Miraldi Fifo	46	47	0	46
M-020	Alpha prototype	All	46	48	2	46
M-021	Requirements Gathering	Andrea Bottoli	47	47	0	47
M-022	Update Design Doc.	Andrea Bottoli	47	48	0	48
M-023	Update Requirem. Doc.	Dzana Kujan	47	48	0	48
M-024	Finalize Math Engine	Lorenzo Pagliari	48	49	1	48
M-025	Web Design	Miraldi Fifo	48	49	1	48
M-026	Status Report	All	49	49	0	48
M-027	UserLoginSystem	Jorn Tillmanns	49	50	1	48
M-028	Finalize Math Engine	Lorenzo Pagliari	49	50	0	49
M-029	Junit tests v1	Miraldi Fifo	49	50	0	49
M-030	Web Site Mockups	Nikola Radisavljevic	49	49	0	49
M-031	Web Site Graphs	Dzana Kujan	49	50	0	49
M-032	Beta Prototype	All	50	51	0	50
M-033	Beta Prototype pres.	Lorenzo Pagliari	51	51	0	51
M-034	Technical documentation	Andrea Bottoli	51	51	0	51
M-035	Acceptance Test Plan	Miraldi Fifo	51	52	0	52
M-036	Test Report	Miraldi Fifo	01	02	1	52
M-037	Final Presentation	All	02	02	0	01
M-038	Final Documentation	All	02	03	1	01
M-039	Final Product	All	02	03	1	01
M-040	Final Questionnaire	All	02	03	1	01

Working Hours

Member	W42	W43	W44	W45	W46	W47	W48	W49	W50	W51	W52	W01	W02	Total
Andrea Bottoli	11	40	50	45	47	68	40	41	14	53	7	8	32	456
Lorenzo Pagliari	10	37	53	51	46	57	37	51	43	54	10	26	17	492
Dzana Kujan	9	36	43	36	27	36	27	49	24	17	2	5	17	328
Marko Brcic	11	40	54	60	28	36	26	15	15	15	11	4	22	337
Jorn Tillmanns	9	37	51	43	20	13	39	16	15	22	18	12	15	310
Nikola Radisavljevic	9	37	45	36	26	35	26	46	25	17	12	7	17	338
Miraldi Fifo	9	38	45	35	16	28	14	18	18	13	12	10	15	271
Ghazaleh Shojaee	-	-	53	13	32	26	-	-	-	-	-	-	-	124
Total	68	265	394	319	242	299	209	236	154	191	72	72	135	2656