		Summary Week Report

Project	Real-Time Bridge Monitoring			Week	48
Responsible	Andrea Bottoli			Date	02.12.2013

## Executive Summary

Timeliness

General Project Status	Fulfillment of Next Milestone
on track	On Schedule

## Results This Week

Activity Owner(s)	Activity	Workload	Fore cast	Result / Comment
All	Monday Meeting	1	2	Internal meeting to discuss problems, project status and questions for customers
All	Thursday Meeting	1	2	Internal meeting to discuss problems, project status and other internal stuffs
All	Lecture Class	2	2	Lecture Class for the alpha prototype presentations
All	Week Report	1	1	Write the week report
Andrea Bottoli, Lorenzo Pagliari	Meeting with customer (Tuesday)	3	2	Meeting with customers to ask them some questions about the project and to gather more information and requirements
Andrea Bottoli, Lorenzo Pagliari	Meeting with supervisors	2	2	Meeting with supervisors to inform about the project and group status and to ask suggestions about the Alpha Prototype presentation
Andrea Bottoli, Lorenzo Pagliari	Meeting with customer (Thursday)	2	2	Meeting with customers to ask them some questions about the project, to gather more information and requirements and to finish the requirements phase
Andrea Bottoli, / Lorenzo Pagliari	Math Engine	20	20	Work on the implementation of the math engine
Andrea Bottoli, Dzana Kujan	Meeting	1	1	Meeting with Project Leader and Team Leader to exchange information, suggestions and to take some decision on how improve the project management
Marco Brcic, Jorn Tillmanns	Parser Implementation	10	10	Implementation of Parser
Dzana Kujan, Nikola Radisavljevic, Jorn Tillmanns	Web Application and Presentation layer	10	10	Work on the graphs and the design of the website, work with JSON, with jsp and with CSSs
Dzana Kujan, Nikola Radisavljevic	Preparing Presentation	10	10	Prepared the Alpha Prototype presentation
Dzana Kujan, Nikola Radisavljevic	Alpha prototype presentation	1	1	Presented the alpha prototype to DSD staff
Andrea Bottoli	Update tasks and meeting agendas	3	3	Updated tasks and issues on the repository; delivered meeting agendas before each meeting
Andrea Bottoli	Customer Meeting Summary	2	2	Summarized new requirements of the customer, with graphs and some explanations
Andrea Bottoli	Summary Week Report	2	2	Write the summary week report
Lorenzo Pagliari	Translation	5	2	Work on the translation of the last changes in Input and Convertions document
Marko Brcic	Work on DAO	6	10	Implemented the parameters entity layers, work on parser module, fixed DAOProvider class
Marko Brcic	Manage Repository	2	4	Manage the repository
Marko Brcic	Manage VM	4	4	Manage the VM
Marko Brcic	Work on Web App	2	2	Deploying the web application
Marko Brcic	Class Diagrams	3	3	Create updated class diagrams
Jorn Tillmanns	User Login System	12	12	Start working on the user login system
Jorn Tillmanns	Update DB	2	2	Update the DB following new requirements
Miraldi Fifo	Junit	9	9	Start working on tests using JUnit

## Activities Planned for Next Period

Activity Owner(s)	Activity	Work load	Result / Comment
All	Monday Meeting	2	Internal meeting to discuss problems, project status and questions for customers
All	Thursday Meeting	2	Internal meeting to discuss problems, project status and replies for customers
All	Lecture	3	DSD lecture
All	Week Report	1	Write the week report
Dzana Kujan, Nikola Radisavljevic, Miraldi Fifo, / Andrea Bottoli, Lorenzo Pagliari	Modify Requirements Document	10	Improve the quality of the requirements document in order to fit more with the new architecture and technologies and requirements
Andrea Bottoli, Lorenzo Pagliari, Marko Brcic, Jorn Tillmanns	Modify Design Document	10	Improve the quality of the design document in order to fit more with the new architecture and technologies and requirements
Andrea Bottoli, Lorenzo Pagliari	Math Engine	30	Continue implementing the math engine and the calculation controller; work also on CalculatedData
Andrea Bottoli, Lorenzo Pagliari, Marko brcic	Calculation Controller and DB	20	Interface the Calculation Controller and the Calculated Data with the DB
Andrea Bottoli, Dzana Kujan	Status Report presentation preparation	10	Prepare the Status Report presentation
Andrea Bottoli, Dzana Kujan	Status Report presentation	1	Present the Status Report to the DSD staff
Dzana Kujan, Nikola Radisavljevic, Miraldi Fifo	Current State View Design	20	Finalize the design of the web page for the Current State View
Dzana Kujan, Nikola Radisavljevic, Miraldi Fifo	History Diagrams Design	20	Finalize the design of the web page for the History Diagrams View
Jorn Tillmanns, Marko Brcic	User Login System	10	Work on the implementation of the user login system
Andrea Bottoli	Meeting with supervisors	2	Meeting with supervisors to inform about the project and group status and to gather some suggestions for the Status Report presentation
Andrea Bottoli	Summary Week Report	2	Write the summary week report
Marko Brcic	Manage VM	4	Continue to manage the VM
Marko Brcic	Manage Repository	4	Continue to manage the repository
Miraldi	JUnit Classes	20	Prepare the classes for make tests on the Math Engine using JUnit tool

## Comments / Experiences / Problems

- Encountered some problems in understanding the new requirements gathered from the Customer
- Encountered some problems in understanding the European Directive for the Constructions
- It's not very simple explain and understand the new requirements and the laws in EU for the constructions
- VM little slow when the parser works; it takes a long for parse the files in input
- The DB is very huge: at this moment, we have more than 11,000,000 tuples in Raw_Data table

## Metrics

Milestones

Id	Milestone Description	Responsible Dept./Initials	Finished week				Metr	Rem
			Plan	Forecast		Actual
				Week	+/-
M-001	Project Plan & Vision	All	42	42	0	43
M-002	Requirements gathering	All	43	43	0	43
M-003	Requirements document	All	43	44	1	43
M-004	System Design	All	43	44	0	43
M-005	Requirement Document	All	44	44	0	44
M-006	Design Document	All	44	44	0	44
M-007	Status Report	All	44	44	0	44
M-008	Organize Repository	Marko Brcic	45	45	0	45
M-009	Team Policies	Marko Brcic	45	45	0	45
M-010	Share telephone number	All	45	45	0	45
M-011	Modify Requirement Doc	Dzana Kujan	45	46	1	45
M-012	Modify Design Doc	Lorenzo Pagliari	45	46	1	45
M-013	Setup tools on PC	All	45	45	0	45
M-014	Change DB	Jorn Tillmanns	45	45	0	45
M-015	Implementation Parser	Jorn Tillmanns	45	45	0	45
M-016	Implementation DAO	Jorn Tillmanns	45	45	0	45
M-017	Start Implementation Math	Andrea Bottoli	45	46	1	45
M-018	Test Parser	Miraldi Fifo	46	47	0	46
M-019	Test Classes alpha prot.	Miraldi Fifo	46	47	0	46
M-020	Alpha prototype	All	46	48	2	46
M-021	Requirements Gathering	Andrea Bottoli	47	47	0	47
M-022	Update Design Doc.	Andrea Bottoli	47	48	0	48
M-023	Update Requirem. Doc.	Dzana Kujan	47	48	0	48
M-024	Finalize Math Engine	Lorenzo Pagliari	48	49	1	48
M-025	Web Design	Miraldi Fifo	48	49	1	48
M-026	Status Report	All	49	49	0	48
M-027	UserLoginSystem	Jorn Tillmanns	49	50	1	48
M-028	Finalize Math Engine	Lorenzo Pagliari	49	50	1	48
M-029	Junit tests	Miraldi Fifo	49	50	1	48
M-030	Web Site Mockups	Nikola Radisavljevic	49	49	0	48
M-031	Web Site Graphs	Dzana Kujan	49	50	1	48
M-032	Beta Prototype	All	50	51	1	48

Working Hours

Member	W42	W43	W44	W45	W46	W47	W48	Total
Andrea Bottoli	11	40	50	45	47	68	40	301
Lorenzo Pagliari	10	37	53	51	46	57	37	291
Dzana Kujan	9	36	43	36	27	36	27	214
Marko Brcic	11	40	54	60	28	36	26	255
Jorn Tillmanns	9	37	51	43	20	13	39	212
Nikola Radisavljevic	9	37	45	36	26	35	26	214
Miraldi Fifo	9	38	45	35	16	28	14	185
Ghazaleh Shojaee	-	-	53	13	32	26	-	124
Total	68	265	394	319	242	299	209	1796